PHASE-3

Internship Management System

PROJECT ESTIMATION AND SCHEDULING

March 30th, 2026

Anvita Rayapati-2024BCS-009

Pooja Luhar-2024BCS-049

Sresshma Nair -2024BCS-073

CS-210 Software Engineering

1. Project Estimation

This document covers estimations for Effort, Duration, Staff, Cost, and Schedule using Function Point Analysis, Intermediate COCOMO, PERT, and Jordan's Staffing Method.

# 2. Functional Point Analysis

In this section we calculate function points for all use cases to evaluate the project size and cost. The system has 4 actors ,Student, Mentor, Employer, and College.

KLOC Estimation

Usp calculation

External Inputs (EI)

| Use case | EI | EO | EQ | ILF | EIF |
| --- | --- | --- | --- | --- | --- |
| Login/register | 2 | 1 | 0 | 1 | 0 |
| Manage Profile | 2 | 1 | 1 | 1 | 0 |
| Upload Resume & other document | 1 | 1 | 0 | 1 | 1 |
| Skill Assessment | 1 | 2 | 1 | 1 | 1 |
| Search companies and requirements | 1 | 1 | 2 | 1 | 0 |
| Apply for Internship | 1 | 2 | 1 | 1 | 0 |
| Attend Guidance Session | 2 | 1 | 0 | 1 | 0 |
| Mock Interview | 2 | 1 | 0 | 1 | 0 |
| View Student Profile | 0 | 1 | 1 | 0 | 0 |
| Submit Review | 2 | 1 | 1 | 1 | 0 |
| Upload Internships | 2 | 2 | 1 | 1 | 1 |
| Customize ATS | 2 | 1 | 1 | 1 | 1 |
| Select Students | 1 | 1 | 1 | 0 | 0 |
| Track Student Progress | 1 | 2 | 1 | 1 | 0 |
| Manage Tie-Up Companies | 2 | 1 | 1 | 0 | 0 |
| Create Report | 1 | 1 | 0 | 1 | 2 |
| TOTAL | 23 | 19 | 11 | 12 | 4 |

Weighted function point calculation

Classify components  as low,high,average  and multiplied by standard IFPUG weight

External Inputs

| Use case | complexity | Count | Weight | total |
| --- | --- | --- | --- | --- |
| Login/register | low | 3 | 3 | 9 |
| Manage Profile | Average | 4 | 4 | 16 |
| Upload Resume & other document | Average | 3 | 4 | 12 |
| Apply for Internship | Average | 3 | 4 | 12 |
| Mock Interview | low | 4 | 3 | 12 |
| Submit Review | Average | 3 | 4 | 12 |
| Upload Internships | Average | 4 | 4 | 16 |
| Customize ATS | High | 2 | 6 | 12 |
| TOTAL |  |  |  | 101 |

External Output

| Use case | complexity | Count | Weight | total |
| --- | --- | --- | --- | --- |
| Skill Assessment Report | Average | 3 | 5 | 15 |
| Internship Recommendation | High | 2 | 7 | 14 |
| Student Progress Report | Average | 4 | 5 | 20 |
| Resume Parser Output | Average | 3 | 5 | 15 |
| Analytics Dashboard | High | 2 | 7 | 14 |
| Placement Report | Average | 3 | 5 | 15 |
| TOTAL |  |  |  | 93 |

External Inquiries

| Use case | complexity | Count | Weight | total |
| --- | --- | --- | --- | --- |
| Search Companies & Requirements | low | 3 | 3 | 9 |
| View Student Profile | low | 3 | 3 | 9 |
| View Internship Status | low | 2 | 3 | 6 |
| Skill Gap Query | Average | 2 | 4 | 8 |
| TOTAL |  |  |  | 32 |

Internal Logical Files

| Use case | complexity | Count | Weight | total |
| --- | --- | --- | --- | --- |
| Student Data | Average | 2 | 10 | 20 |
| Internship Listings | Average | 2 | 10 | 20 |
| Company / Employer Data | Average | 2 | 10 | 20 |
| Mentor / Session Data | low | 2 | 7 | 14 |
| Assessment & Reports | Average | 2 | 10 | 20 |
| Application Records | low | 2 | 7 | 14 |
| TOTAL |  |  |  | 108 |

External Interface Files

| Use case | complexity | Count | Weight | total |
| --- | --- | --- | --- | --- |
| Resume Parser API | low | 1 | 5 | 5 |
| Job Portal / LinkedIn Feed | low | 1 | 5 | 5 |
| Email / Notification Service | low | 1 | 5 | 5 |
| College ERP System | Average | 1 | 7 | 7 |
| TOTAL |  |  |  | 22 |

Unadjusted Function Points

UFP =  EI +EO +EQ + ILF +EIF

UFP =  101+93+32+22+108= 356

Value Adjustment Factor

General System Characteristics rated across 14 factors (data communications, distributed processing, performance, AI/ML complexity, reusability, etc.) gave a Total GSC = 35.

VAF = 0.65 + (0.01 *  35) = 1.00

Final Function Points

FP = UFP * VAF = 356 * 1.00 = 356

Conversion to KLOC

Using 40 LOC/FP standard conversion factor by using Python

LOC = 356 × 40 = 14240 =  14.24 KLOC

| USP | 356 |
| --- | --- |
| VAF | 1.00 |
| FP | 356 |
| LOC | 14240 |
| KLOC | 14.24 |

Intermediate COCOMO

Project Classification

Project Type

Organic,  it needs small academic team, moderate familiarity with requirements, and has no strict deadline constraint.

| Constant a | 2.4 |
| --- | --- |
| Exponent b | 1.05 |
| KLOC | 7.12 |

Cost Drivers and EAF Calculation

| category | Driver | Rating | Multiplier |
| --- | --- | --- | --- |
| Product | Required reliability | high | 1.15 |
| Product | Product Complexity | High | 1.15 |
| Product | Database Size | High | 1.08 |
| hardware | Execution Time Constraint | Nominal | 1.00 |
| hardware | Main Storage Constraint | Nominal | 1.00 |
| Personnel | Programmer Capability | high | 0.86 |
| Personnel | Analyst Capability | high | 0.86 |
| Personnel | Applications Experience | low | 1.13 |
| Project | Use of Software Tools | High | 0.91 |
| EAF |  |  | 1.03 |

EAF = 1.15 * 1.08 *1.15 * 1.00 * 1.00 * 0.86 * 0.86 * 1.13 * 0.91

= 1.2420 * 1.15 * 0.7396 * 1.13 * 0.91  =  1.03

Effort Estimation

E = a* (KLOC)^b * EAF

= 2.4 * (14.24)^1.05 * 1.03

= 2.4 * 15.89 * 1.03  =  39.29 PersonMonths

3.4 Development Time

T = 2.5 * (E)^0.38 = 2.5 * (39.29)^0.38 = 2.5 *4.00  = 10 months

3.5 Recommended Team Size

Team Size = E / T = 39.29 / 10  =  3members

Cost Estimation

Assuming 1 PersonMonth = 160 working hours

developer rate = Rs.500/hr

Total Hours = 39.29 *160 = 6286 hrs

Total Cost  = 6286 * 500 = Rupees 3143200

| Effort | 39.29 PersonMonths |
| --- | --- |
| Development Time | 10 Months |
| Team Size | 3 Members |
| Total Hours | 6286 hrs |
| Total Cost | Rs 3143200 |

Staff Scheduling

| Member | role | Phase responsibility |
| --- | --- | --- |
| Anvita RAYAPATI | Frontend Development and Testing | Design, Frontend, Testing and Integration |
| Pooja Luhar | Backend Development + AI Integration | Requirements, Design, Backend, AI |
| Sreeshma Chandrasekharan Nair | Database + Documentation+ QA | Design, Database and Documentation |

| Phase | Duration | Assigned To |
| --- | --- | --- |
| Requirement Analysis | 2 weeks | All Members |
| System Design | 2 weeks | All Members |
| Development which includes Frontend +Backend + AI | 2 weeks | Anvita, Pooja |
| Database Design & Integration | 2 weeks | Sreeshma, Pooja |
| Testing & QA | 2 weeks | Anvita , Sreeshma |
| Documentation & Review | 2 weeks | Sreeshma |

PERT Chart

PERT is used to estimate the project duration using three time estimates per task keeping in mind scheduling uncertainty.

TE = ( O + 4M + P ) / 6

O = Optimistic

M = Most Likely

P = Pessimistic

Task Breakdown and TE

| TASK | O(weeks) | M(weeks) | P(weeks) | TE(weeks) |
| --- | --- | --- | --- | --- |
| Requirement Analysis | 1 | 2 | 3 | 2.00 |
| System Design | 2 | 3 | 5 | 3.17 |
| Development | 6 | 9 | 14 | 9.33 |
| Testing & QA | 2 | 3 | 5 | 3.17 |
| Documentation | 1 | 1 | 2 | 1.17 |

Total Duration=18.84 weeks

Individual TE Calculations

Requirement Analysis	:  TE = (1 + 4×2 + 3) / 6  = 12/6 = 2.00

System Design	:  TE = (2 + 4×3 + 5) / 6  = 19/6 = 3.17

Development       	:  TE = (6 + 4×9 + 14) / 6 = 56/6 = 9.33

Testing & QA      	:  TE = (2 + 4×3 + 5) / 6  = 19/6 = 3.17

Documentation     	:  TE = (1 + 4×1 + 2) / 6  =  7/6 = 1.17

Total Project Duration

Total = 2.00 + 3.17 + 9.33 + 3.17 + 1.17 = 18.84 weeks = 19 weeks = 4.75 months

Critical Path

Total Duration = 19 weeks (4.75 months)

5. Estimation using Jordan's Model

Jordan’s model determines how team members should be allocated to a project. The staffing level first increases, reaches its highest point near the middle, and then decreases towards the end. This helps in using resources efficiently according to the workload at each stage.

5.1 Given Values (from COCOMO)

| Total Effort (E) | 39.29 Person-Months |
| --- | --- |
| Project Duration (T) | 10 Months |

5.2 Staffing Calculations

(a)  Average Staffing

M_avg = E / T = 39.29 / 10  =  3.93  =  4 persons

(b)  Peak Manpower

M_peak = 2E / T = 78.58 / 10  =  7.86  =  8 persons (at midpoint)

(c)  Staffing Function

m(t) = (2 x M_peak / T) x t           [0 <= t <= T/2]

= (2 x 7.86 / 10) x t  =  1.57t

m(t) = (2 x M_peak / T) x (T - t)     [T/2 < t <= T]

= 1.57 x (10 - t)

5.3 Staffing Over Time

| Time (Months) | Manpower m(t) |
| --- | --- |
| 0 | 0 |
| 1 | 1.57 |
| 2 | 3.14 |
| 3 | 4.71 |
| 3.5 | 5.50(peak) |
| 4 | 4.71 |
| 5 | 3.14 |
| 6 | 1.57 |
| 7 | 0 |

Staff gradually increases in the starting phases like requirements, design and development. It reaches the highest point around month 5 when most of the main development and AI work is happening. After that, the number of people slowly decreases during testing and documentation. This way, resources are used properly according to the workload at each stage.

5.4 Cost Estimation

Cost is consistent with the COCOMO result:

Total Cost = Rs. 31,43,200

6. Final Summary

| FP (Final) | 356 |
| --- | --- |
| KLOC (Python, 40 LOC/FP) | 14.24 |
| Effort (Intermediate COCOMO) | 39.29 Person-Months |
| Development Duration (COCOMO) | approx. 10 Months |
| Total Duration (PERT) | approx. 19 weeks (4.75 months) |
| Average Staff (Jordan) | 4 Members |
| Peak Staff (Jordan) | approx. 8 Members |
| Total Cost | Rs. 31,43,200 |

Function point analysis estimate the system to be around 356 FP. Since we are using Python (40 LOC per FP), this comes to roughly 14.24 KLOC. This size makes sense because the system includes AI/ML features, multiple user roles, and real-time tracking.

Using the Intermediate COCOMO model and considering factors like high reliability, large database and complex AI logic, along with an effort adjustment factor (EAF = 1.03), the total effort comes out to about 39.29 person-months. The project is expected to take around 10 months with an estimated cost of Rs. 31,43,200.

According to PERT analysis, the project can be completed in about 19 weeks in the best case if everything goes smoothly and sequentially. Jordans model suggests that the team size should increase gradually reach a peak of around 8 members in the middle of the project, and then decrease towards the end.

Overall, these estimations show that the project is feasible and can be completed properly within the given academic timeline if everything goes smooth.